## Sheet1
Task No. | Task Title | Estimated Hours | Actual Hours | Pair-Programming Team
1.1 | Project Outline | 10 | 8 | TEAM
1.2 | User Stores | 1 | 1 | TEAM
1.3 | Requirements gathering
1.3.1 | Testing requirements | 2 | 2 | TEAM
1.3.2 | Software requirements | 2 | 3 | TEAM
1.4 | System naming standards | 0.5 | 0.5 | TEAM
1.5 | Formalize repository structure | 0.5 | 0.5 | TEAM
1.6 | Outline task breakdown | 1 | 2 | TEAM
1.7 | Form programming pairs and task sign-up | 0.5 | 0.5 | TEAM
2.1 | Define iteration features | 2 | 4 | TEAM
2.2 | Generate CRC cards | 2 | 1 | TEAM
x.1 | Test-driven development (TEMPLATE FOR ACTUAL USE)
x.1.1 | Design tests for feature iterations | ? |  | <member names>
x.1.2 | Implement code to fulfill all tests | ? |  | <member names>
x.2 | Ensure required documentation complete | 1.5 |  | <member names>
x.3 | Release code and merge to repository | 1 |  | <member names>
x.4 | Refactor repository code | 2 |  | <member names>
x.5 | Repeat development phase for all discrete feature iterations until completed | N/A
3.1 | GraphGeneration iteration branch:
3.1.1 | Design tests for feature iterations | 2 | 2 | Daniel, Connor, Chris
3.1.2 | Implement code to fulfill all tests | 10 | 12 | Daniel, Connor, Chris
3.2 | Ensure required documentation complete | 1.5 | 1 | Daniel, Connor, Chris
3.3 | Release code and merge to repository | 1 | 0.5 | Daniel, Connor, Chris
3.4 | Refactor repository code | 2 | 0.5 | Daniel, Connor, Chris
4.1 | DialogueGraph iteration branch:
4.1.1 | Design tests for feature iterations | ? |  | Nate, Felipe
4.1.2 | Implement code to fulfill all tests | ? |  | Nate, Felipe
4.2 | Ensure required documentation complete | 1.5 |  | Nate, Felipe
4.3 | Release code and merge to repository | 1 |  | Nate, Felipe
4.4 | Refactor repository code | 2 |  | Nate, Felipe
5.1 | IOParsing iteration branch:
5.1.1 | Design tests for feature iterations | 2
5.1.2 | Implement code to fulfill all tests | 12
5.2 | Ensure required documentation complete | 1.5
5.3 | Release code and merge to repository | 1
5.4 | Refactor repository code | 2
4.1 | Acceptance testing | 2 |  | TEAM
4.2 | Requirements revisions | 2 |  | TEAM
4.3 | Repeat design-development-review cycle for requirements additions or revisions | N/A |  | TEAM
4.4 | Finalize report |  |  | TEAM
4.5 | Release software | 0.5 |  | TEAM
|  | Budget: | Actual:
|  | 65.5 | 38.5